## Execution Plan
Execution Plan 8/13/2024 - 12/5/2024
| 2024-09-03 | 2024-09-10 | 2024-09-17 | 2024-09-24 | 2024-10-01 | 2024-10-08 | 2024-10-15 | 2024-10-22 | 2024-10-29 | 2024-11-05 | 2024-11-12 | 2024-11-19 | 2024-11-26 | 2024-12-03 | 2024-12-05 | Date
CONOPS Report | [12 empty] | Not Started |  |  | 2024-09-15
FSR, ICD, Milestones, & Validation Plan | [12 empty] | In Progress |  |  | 2024-09-26
Project Introduction Presentation | [12 empty] | Completed |  |  | 2024-10-02
Schematic Layout | [12 empty] | Behind Schedule |  |  | 2024-09-24
Subsystem Introduction Project | [15 empty] | 2024-10-15
Order Parts | [15 empty] | 2024-10-08
Software Code | [15 empty] | 2024-10-20
Hardware Code | [15 empty] | 2024-10-28
PCB Layout | [15 empty] | 2024-10-15
Order PCBs | [15 empty] | 2024-10-29
Project Update Presentation | [15 empty] | 2024-10-21
Firmware Validation / Debugging w/ breadboard | [15 empty] | 2024-10-27
Database Integration | [15 empty] | 2024-11-03
PCB Assembly | [15 empty] | 2024-11-06
Final Presentation | [15 empty] | 2024-11-18
PCB Validation / Debugging | [15 empty] | 2024-11-25
Project Subsystem Demonstration | [15 empty] | 2024-11-26
Final Report | [15 empty] | 2024-12-05

## Validation Plan
Validation Plan
Paragraph # | Test Name | Success Criteria | Methodology | Status | Responsible Engineer(s)
3.2.1.1 | Standby Wake-Up Miss Rate | The maximum number of miss trigger incidents within the sensor's field of view will be 15% or less. | The sensors will be trigger tested at different distances to determine % of miss rates | UNTESTED | Romi Gilat
3.2.1.2 | False Positive Rate | Within the sensor system, the false positive rate will be less than 15% in case of small animals or critters walking within the range. | Sensors will be trigger tested to check for false positive rates | UNTESTED | Romi Gilat
3.2.1.3 | Battery Operating Time | The operating time of the 12V Lead-Acid battery shall be between 10 and 20 hours. | Battery will be tested to check depletion time while the system is running | UNTESTED | Nick Miller
3.2.1.4 | Solar Charging Time | The solar charging time shall be between 4 and 6 hours. | This will be tested by fully charging the batteries under full sunlight. | UNTESTED | Atahan
3.2.2.1 | System Area | The system area shall include the rooftop, foyer and exterior of a household. | The area of instillation needs to support the solar panels, batteries, and wiring | UNTESTED | Atahan
3.2.2.2 | Installation | The solar panel installation will be done up to National Electrical Code (NEC), International Building Code (IBC), and International Fire Code (IFC), along with the mounting of the system 45 degrees tilted offset from the ground level for optimal sunlight. The batteries will be done to NEC and be placed within the wall close to the control unit. The control unit will be placed within the wall as well, with wiring connecting the exterior and interior sensor units. These will be mounted on the ceiling to ensure optimal field of view. | Instillation will be done in optimal angel to the sun within area of use | UNTESTED | All
3.2.2.3 | Mounting | The automatic solar lighting system will consist of three primary mounted components: solar panels, an indoor sensor with integrated light bulbs, and an outdoor sensor with integrated light bulbs. The interior and exterior lighting units are designed to be relatively lightweight, eliminating the need for substantial structural support, such as interior beams, for installation. Meanwhile, the solar panels will be strategically positioned on the roof to maximize exposure to sunlight. | The mounting will be completed in 404 | UNTESTED | All
3.2.3.1 | Inputs | The Automatic Solar Lighting System is designed to receive multiple inputs across its different subsystems. The Power Generation subsystem solar power input via the photovoltaic panels. The app receives information on the status of the light as well as various status updates for each of the included subsystems and their performance. The Buck Converter/Inverter subsystem intakes a certain DC voltage and transforms it into a voltage that is suitable for usage with the MCU or the lighting. | These inputs need to consistntly match throughout the system to ensure connectivity | UNTESTED | Atahan, Nick, Romi
3.2.3.1.1 | Power Consumption | The system shall consume approximately 18 Watts, 9 Watts per light bulbs. | Power consumption will be tested by running the system on fully charged batteries until they are depleted, measuring the duration it takes for the batteries to be exhausted | UNTESTED | Nick Miller
3.2.3.1.2 | Input Voltage Level | The input voltage level shall be +10 VDC to +14 VDC. | Check the voltage outputs using a voltmeter. | UNTESTED | Nick Miller
3.2.3.1.3 | External Commands | The Automatic Solar Lighting System shall document all external commands in the appropriate ICD. | These commands will be verified through the IDC using testing | UNTESTED | Cedar Maxwell
3.2.3.2.1 | Data Output | The Automatic Solar Lighting System will output the status of the porch and foyer lights by means of the mobile application. | This will be tested by turning on the light and seeing if the trigger is sent to the app | UNTESTED | Cedar Maxwell
3.2.3.2.2 | Diagnostic Output | The MCU will transmit diagnostic data to the app for display. | The MCU and app will display mutliple outputs based on different tests | UNTESTED | Cedar Maxwell, Romi Gilat
3.2.3.2.3 | Connectors | The Automatic Solar Lighting System will use the American National Standard for Electrical Connectors ANSI C119.6-2011. | connectors will be completed in 404 | UNTESTED | All
3.2.3.2.4 | Wiring | The Automatic Solar Lighting System will follow the guidelines set forth by the National Electrical Code regarding electrical wiring. The standard applications of electrical systems is in the article NFPA 70 (NEC). | Electrical wiring will be done in 404 | UNTESTED | All
3.2.4.1 | Altitude | The Automatic Solar Lighting System shall be able to operate efficiently at altitudes around 300 feet. | This was decided based on normal house height and texas altitude | UNTESTED | Nick, Romi, Atahan
3.2.4.2 | Thermal | The Automatic Solar Lighting System shall be able to operate efficiently at temperatures ranging from 0℃ to 70℃. The microcontroller unit will be located indoors, where the temperature is expected to range from 0°C to 70°C. The sensor system will be used both indoors and outdoors, and is rated for temperatures from -40°C to 85°C. | This was decided based on compoenets picked | UNTESTED | Nick, Romi, Atahan
3.2.4.3 | Humidity | The sensor unit will function up to 90% humidity for proper functioning.The sensors themselves need to be placed in a water proof, sealed container that will prevent the electronics from getting drenched. | This was decided based on Texas's weather forcaste | UNTESTED | All